# Engineering Pulse — Org Adservio ADS Q3 W28 - 13-17 Jul

Aggregated sprint ADS Q3 W28 - 13-17 Jul • deduplicated roll-up across included teams

This org roll-up aggregates deduplicated frozen issue facts across 4 team snapshots. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 24/61 visible items. The org roll-up absorbed noise reasonably well — 11/32 added items were closed — but predictability on committed work was only 35.8% (19/53), and bugs made up 33.3% of completed items. The main drag was execution system quality, not readiness: 9/34 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 35.8% (19/53) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 64.2% (34/53) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 45.5% (15/33) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 76.5% (13/17) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 52.5% (32/61) | Added items ÷ all visible items |
| Added work closure | 11/32 | All added items marked Done |
| Reactive load (bug share) | 33.3% (8/24) | Completed bugs ÷ all completed work |
| Planning quality | 24.5% (13/53) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

Across included teams, the sprint did not fail; it traded predictability for responsiveness. 11/32 added items were closed, but that responsiveness came with 33.3% bug share and diluted committed completion.

The miss pattern is concentrated: 16 partial-completion carryovers, 3 dependency-driven misses, and 12 committed items that never really started.

Most misses were not caused by poor readiness. 9 of the 34 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 5 | 3 | 0 | 0 | 8 | 33.3% |
| Task | 6 | 1 | 0 | 0 | 7 | 29.2% |
| Bug | 2 | 6 | 0 | 0 | 8 | 33.3% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 53 | Explicit promise set |
| Committed done | 19 | Closed as promised |
| Committed carry over | 34 | Unfinished promise |
| Committed items marked Ready | 13 | Planning-quality input |
| Carryovers marked Ready | 9 | Ready did not guarantee finish |
| Carryovers not started | 12 | Execution focus gap |
| Carryovers started but unfinished | 15 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-2590 — Bug — [Students] - Trebuie inlocuit articolul de la model import automat-date de completare si sa se deschida articolul din manualul de utilizare daca de da click pe linkul respectiv | Marian Andrei | In Progress | Partial completion |
| ADS-3896 — Bug — [Classes][Homework] -Problema la Trimiterea Temelor Corectate din aplicatia de mobil | Ivan Ioana | To Do | Not started |
| ADS-4007 — Bug — [BE][Subscriptions] - Comportament ciudat featureflags in cazul in care sunt dezactivate subscriptiile | Dragoș Ivan | To Do | Not started |
| ADS-4328 — Story — Headers in Mobile App | Dragoș Ivan | To Do | Not started |
| ADS-5808 — Bug — [MOB][Wellbeing] - Parintele nu poate vizualiza testele de autocunoastere pe mob | Antoci Razvan | To Do | Not started |
| ADS-6142 — Story — [Registre Matricole] -US1.1 Creare volume si asociere studenti incadrati | stefan.achim | In Progress | Partial completion |
| ADS-6159 — Story — Notification Center for Mobile | Dragoș Ivan | In Progress | Partial completion |
| ADS-6201 — Story — Log formatting - node.js, subscriptions | Dragoș Ivan | To Do | Not started |
| ADS-6438 — Task — [BE][UNI] - Sincronizare ID-uri Ani universitari/scolari - UNI/preuni - master | andrei.alexandru | Ready to merge | Partial completion |
| ADS-6675 — Story — [Financiar] - Managementul penalitatilor | George Murgoci | In Progress | Partial completion |
| ADS-6694 — Story — [MOB] - Test parenting |  | In Progress | Partial completion |
| ADS-7343 — Task — [Stiri] - Distribuie Updates | Alex Murarescu | To Do | Partial completion |
| ADS-7474 — Task — [FE] - Optimizare viteză de încărcare pagini | Dragoș Ivan | To Do | Partial completion |
| ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte | Cristina Condrea | Testing | Partial completion |
| ADS-7535 — Story — [FE] - Download Adeverinta de absolvire | Ionut Ciolan | In Progress | Dependency delay |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | Ionut Ciolan | In Progress | Bug / rework pressure |
| ADS-7816 — Story — [SIIIR] - Import clase | Marian Andrei | In Progress | Partial completion |
| ADS-7831 — Story — [Spike] - Mobile app cold start | stefan musat | To Do | Not started |
| ADS-7849 — Story — Stergere date S3 | Cojan Paul-Catalin | In Progress | Partial completion |
| ADS-7884 — Story — [MOB] - Web bridge SDK | stefan musat | Testing | Partial completion |
| ADS-7890 — Story — [BE PHP][Cazari] - Stingerea obligatiilor din E-taxe | Ionut Ciolan | Ready for testing | Dependency delay |
| ADS-7907 — Task — [BE] Refactoring SQL_CALC_FOUND_ROWS | Marian Andrei | In Progress | Partial completion |
| ADS-8067 — Improvement — [Incadrare] Refactoring React & API | Andrei Dragan | In Progress | Late start / sequencing |
| ADS-8068 — Story — [MOB] - Încheiere situatie | Stefan Agrigoroaei | To Do | Partial completion |
| ADS-8071 — Story — Teste automate flow Subscripții | Edgar Alexa | In Progress | Partial completion |
| ADS-8104 — Story — [BE-PHP] - Gestiunea cazarilor de vara | Ionut Ciolan | Merged | Dependency delay |
| ADS-8105 — Story — Impartirea pe module | Ivan Ioana | In Progress | Partial completion |
| ADS-8118 — Bug — [BE] - Lipsa nota si catalog deschis pe restantieri | andrei.alexandru | To Do | Not started |
| ADS-8147 — Bug — [BE] - Nu apar studentii pe sesiunea 2 | andrei.alexandru | To Do | Not started |
| ADS-8153 — Bug — [Prod][TUIASI][accommodations-api] Student balance export returns HTTP 500 when mPDF hits pcre.backtrack_limit | andrei.alexandru | To Do | Not started |
| ADS-8186 — Bug — [Prod][AWS][accommodations-api] External person create returns 500 after partial create when fallback faculty is hidden by scope | andrei.alexandru | To Do | Bug / rework pressure |
| ADS-8209 — Bug — [Prod][AWS][legacy-web] GET /api/v2/fisiere/view returns HTTP 500 when M_fisiere.php calls query() on null | Marian Andrei | To Do | Not started |
| ADS-8223 — Bug — [Prod][AWS][ingress] POST /api/v2/fisiere/upload maps backend 400 to HTTP 500 - 10/72h | Cojan Paul-Catalin | To Do | Not started |
| ADS-8244 — Bug — [Cazari] - Sold gresit in obligatie de plata fata de fisa studentului | andrei.alexandru | To Do | Not started |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 16 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 3 | Capacity protection or dependency timing created slip |
| Not started | 12 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 15 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Included teams in this org pulse: Mobile, Team 1, Team 2, University.

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 52 | 52 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 66 | 66 issues in the Friday review snapshot |
| Normalized sprint fact base | 61 | 61 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.