# Engineering Pulse — University ADS Q3 W28 - 13-17 Jul

Planned sprint ADS Q3 W28 - 13-17 Jul • planning snapshot + end-of-sprint outcome snapshot

This version uses the planning snapshot as the promise set and the outcome snapshot as the result set. Count metrics link to snapshot-exact JQL result pages. Jira IDs in the report link to live Jira issues.

# Executive summary

Yellow. The sprint closed 11/23 visible items. The team absorbed noise well — 1/4 added items were closed — but predictability on committed work was only 45.5% (10/22), and bugs made up 18.2% of completed items. The main drag was execution system quality, not readiness: 2/12 carryovers had been marked Ready at planning time.

# Top-line metrics

| Metric | Value | How to read it |
| --- | --- | --- |
| Committed completion | 45.5% (10/22) | Planned items marked Done ÷ all planned committed items |
| Committed carryover | 54.5% (12/22) | Planned committed carryovers ÷ all planned committed items |
| Finish predictability | 43.8% (7/16) | Finish-intent planned items done ÷ all finish-intent planned items |
| Progress predictability | 50.0% (3/6) | Progress items that behaved as intended by carrying |
| Added-during-sprint load | 17.4% (4/23) | Added items ÷ all visible items |
| Added work closure | 1/4 | All added items marked Done |
| Reactive load (bug share) | 18.2% (2/11) | Completed bugs ÷ all completed work |
| Planning quality | 18.2% (4/22) | Committed items marked Ready ÷ all committed items |
| Workflow-truth mismatches | 0 | Items marked Done in review while workflow status remained non-final |

# Engineering readout

The sprint did not fail; it traded predictability for responsiveness. 1/4 added items were closed, but that responsiveness came with 18.2% bug share and diluted committed completion.

The miss pattern is concentrated: 3 partial-completion carryovers, 3 dependency-driven misses, and 4 committed items that never really started.

Most misses were not caused by poor readiness. 2 of the 12 carryovers had been marked Ready, so the stronger hypothesis is breakdown, sequencing, and capacity protection rather than simple scoping immaturity.

# Delivered work mix

| Type | Planned | Added | Stretch | Unclear | Total done | Done % |
| --- | --- | --- | --- | --- | --- | --- |
| Story | 5 | 1 | 0 | 0 | 6 | 54.5% |
| Task | 3 | 0 | 0 | 0 | 3 | 27.3% |
| Bug | 2 | 0 | 0 | 0 | 2 | 18.2% |

# Committed work: plan vs execution

| Signal | Value | Why it matters |
| --- | --- | --- |
| Committed items | 22 | Explicit promise set |
| Committed done | 10 | Closed as promised |
| Committed carry over | 12 | Unfinished promise |
| Committed items marked Ready | 4 | Planning-quality input |
| Carryovers marked Ready | 2 | Ready did not guarantee finish |
| Carryovers not started | 4 | Execution focus gap |
| Carryovers started but unfinished | 4 | Work moved, but did not close |

# Carryover pattern

| Jira item | Owner | Status | Why it carried |
| --- | --- | --- | --- |
| ADS-6142 — Story — [Registre Matricole] -US1.1 Creare volume si asociere studenti incadrati | stefan.achim | In Progress | Partial completion |
| ADS-6438 — Task — [BE][UNI] - Sincronizare ID-uri Ani universitari/scolari - UNI/preuni - master | andrei.alexandru | Ready to merge | Partial completion |
| ADS-7534 — Story — [FE/BE][Adeverinte absolvire] - Flow generare adeverinte | Cristina Condrea | Testing | Partial completion |
| ADS-7535 — Story — [FE] - Download Adeverinta de absolvire | Ionut Ciolan | In Progress | Dependency delay |
| ADS-7666 — Bug — accommodations-api: shared HTTP 500 burst on POST /api/v2/accommodations/dorms/list and related endpoints - 16 hits/20m | Ionut Ciolan | In Progress | Bug / rework pressure |
| ADS-7890 — Story — [BE PHP][Cazari] - Stingerea obligatiilor din E-taxe | Ionut Ciolan | Ready for testing | Dependency delay |
| ADS-8104 — Story — [BE-PHP] - Gestiunea cazarilor de vara | Ionut Ciolan | Merged | Dependency delay |
| ADS-8118 — Bug — [BE] - Lipsa nota si catalog deschis pe restantieri | andrei.alexandru | To Do | Not started |
| ADS-8147 — Bug — [BE] - Nu apar studentii pe sesiunea 2 | andrei.alexandru | To Do | Not started |
| ADS-8153 — Bug — [Prod][TUIASI][accommodations-api] Student balance export returns HTTP 500 when mPDF hits pcre.backtrack_limit | andrei.alexandru | To Do | Not started |
| ADS-8186 — Bug — [Prod][AWS][accommodations-api] External person create returns 500 after partial create when fallback faculty is hidden by scope | andrei.alexandru | To Do | Bug / rework pressure |
| ADS-8244 — Bug — [Cazari] - Sold gresit in obligatie de plata fata de fisa studentului | andrei.alexandru | To Do | Not started |

# Miss pattern summary

| Pattern | Count | What it suggests |
| --- | --- | --- |
| Partial completion | 3 | Breakdown / sizing / stage-gating was not tight enough |
| Dependency delay | 3 | Capacity protection or dependency timing created slip |
| Not started | 4 | A committed item remained outside execution focus |
| In Progress / Code Review carryovers | 4 | Most misses were moving, but not closing |

# Workflow-truth mismatches

Items marked Done in the sprint-review field while Jira workflow status was still non-final.

| Jira item | Status | Intent |
| --- | --- | --- |
| None |  |  |

# Executive follow-up questions

| Question | Why this matters | What evidence to ask for |
| --- | --- | --- |
| Why did committed items carry over despite planning readiness? | This tests execution quality rather than just scope quality. | Show carryovers split by progress continuation, dependency, and not-started. |
| Are Progress items being managed intentionally? | Progress items are allowed to continue, but the continuation should be visible and controlled. | Show the original slice and the specific landing expectation for each item. |
| Is added work a healthy responsiveness level or chronic interruption? | High responsiveness can hide systemic instability and diluted predictability. | Show which added items were urgent/reactive versus discretionary scope change. |
| Can we trust Done in review when workflow is still non-final? | Workflow-truth gaps reduce trust and make completion easy to game. | Show the exact mismatches and the completion rule to enforce next sprint. |

Usage note: start with the top-line metrics, then use the traceability links to answer these questions with issue-level evidence.

# Snapshot and fact-base list links

| Snapshot | Issue count | Link |
| --- | --- | --- |
| Planning snapshot raw list | 20 | 20 issues in the planning snapshot |
| Sprint review / outcome snapshot raw list | 23 | 23 issues in the Friday review snapshot |
| Normalized sprint fact base | 23 | 23 issues used for metrics and drill-down |

Planning and outcome are separate frozen moments.

Metric tables use the normalized sprint fact base, which keeps planning-only misses and outcome-only additions visible for traceability.

# Evidence artifacts

| Artifact | Link |
| --- | --- |
| Issue audit register | Open issue-level audit CSV |
| Metric lineage | Open metric lineage CSV |
| JQL traceability register | Open JQL traceability CSV |
| Sprint metrics JSON | Open sprint metrics JSON |

These companion artifacts keep the pulse debuggable when a leader wants the exact rows behind a metric or a count.